## Sheet1
title Timeline-Capstone-Part-B
section | Time-Allocated
Activity Name | State Of The Activity | Nickname | Date | Length Of Activity
Holiday | done | weekNull | 2018-07-02 | 7d
Week 00 | done | week0 | 2018-07-09 | 7d
Week 01 | done | week1 | 2018-07-16 | 7d
Week 02 | done | week2 | 2018-07-23 | 7d
Week 03 | done | week3 | 2018-07-30 | 7d
Week 04 | active | week4 | 2018-08-06 | 7d
Week 05 | active | week5 | 2018-08-13 | 7d
Week 06 | active | week6 | 2018-08-20 | 7d
Break Week | active | weekBreak | 2018-08-27 | 7d
Week 07 | active | week8 | 2018-09-03 | 7d
Week 08 | active | week9 | 2018-09-10 | 7d
Week 09 | active | week10 | 2018-09-17 | 7d
Week 10 | active | week11 | 2018-09-24 | 7d
Week 11 | active | week12 | 2018-10-01 | 7d
Week 12 | active | week13 | 2018-10-08 | 7d
Week 13 | active | week14 | 2018-10-15 | 7d
section | Assesment-Tasks
Activity Name | State Of The Activity | Nickname | Date | Length Of Activity
Completion Plan | crit | after week3 |  | 7d
Proffesional Practice & Contribution | crit | after week12 |  | 4d
Final Report | crit | after week11 |  | 7d
Presentation | crit | after week13 |  | 3d
section | Software-Android
Activity Name | State Of The Activity | Nickname | Date | Length Of Activity
Joining Protocol Re-Oriented | done | after weekNull |  | 3d
Discovery Protocol Prototype | done |  |  | 7d
Testing Joining Interaction | done |  |  | 7d
Testing Discovery Interaction | active |  |  | 7d
Software design on the fetching the metric | active |  |  | 7d
Verification on Joining & Discovery Interaction | active |  |  | 12d
Documentation | active |  |  | 3d
Realtime Graph Adapter | active |  |  | 7d
Data Fetch from the API inside from the MCU | active |  |  | 7d
section | Software-ESP8266
Activity Name | State Of The Activity | Nickname | Date | Length Of Activity
Re-Oriented Joining Protocol | done | after weekNull |  | 3d
Discovery Protocol Integration | done |  |  | 7d
Integrating Joining and Discovery | done |  |  | 7d
Design on a bounce diagram on metric | active |  |  | 7d
Documentation | active |  |  | 3d
Software to send out metrics every 1 second | active |  |  | 7d
Buffer Implementation to Record Humid and Temp Every Hour In The MCU | active |  |  | 7d
Buffer Implementation to Record Humid and Temp Wihtin the last two hours with resolution of 1 minutes | active |  |  | 7d
section | Hardware-PCB
Activity Name | State Of The Activity | Nickname | Date | Length Of Activity
Testing Relay | done | after weekNull |  | 3d
Reoriented PCB Position | done |  |  | 3d
Consulted PCB Position | done |  |  | 3d
Finalizing PCB | done | PCBFinalized | 2018-07-20 | 4d
Deploy PCB to production | active | FinalizingPCB | 2018-07-24 | 20d
MidPoint PCB Deployment Days | active | MidPoint |  | 1d
Assembly | active |  |  | 7d
Testing PCB | active |  |  | 10d
Validation | active |  |  | 10d
section | Ordering-Hardware
Activity Name | State Of The Activity | Nickname | Date | Length Of Activity
Order and buy waterproof temperature sensor | active | after MidPoint |  | 14d
Order and buy enclosure for wireless sensor | active | after MidPoint |  | 7d
Order and buy the input terminals | active | after MidPoint |  | 7d